## Slide 1: Sellers Ave. Bridge Replacement over AMTRAK ECMS 15306 Ridley Park Borough, Delaware County
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 2: Closed July 20, 2022
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 3: - Traffic will remain detoured over the Swarthmore Ave. Bridge for the duration of the Project - Improved signage to be installed next month
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 4: New Bridge/Project Design includes: - (2) 12’ Vehicle Lanes - (2) 8’ Sidewalks - (6) Sidewalk Luminaires - New water and communication lines - Increased Load Rating (from 3T to 102T) - Improved Fencing - (11) ADA Ramps - Improved Drainage - Intersection Improvements (incl. signals) - Full Depth Reconstruction of Ridley and Hinckley Aves.
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 5: New Bridge
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 6: New Bridge
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 7: New Bridge
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 8: New Bridge
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 9: Bid Results March 2, 2023 Road-Con, Inc. (low bidder) $ 9.8M * Lowest of three bids
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 10: Contract Awarded March 14, 2023 Notice to Proceed April 10,2023 Bridge Open July 1, 2026 Project Completion (planting season) June 30, 2027
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 11: Funding 100% Federal Minority Participation 10% or $980K Trainees 1 Required Wages Prevailing Rates (certified payrolls and wage checks) ADA Compliant 11 new ramps
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 12
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 13: AMTRAK (2023)
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 14: AMTRAK (2023) - Shielding - (2) 48” dia. Caissons 17’ deep - Fabricate and Erect new catenary - Install new AMTRAK power hardware - Re-route power and remove old from bridge
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 15: Stage 1A (1st Half 2024) - Temporary Pedestrian Bridge - Design by Contractor - 5’ wide / 42” handrails / min 8’ high fencing - Utilities to be temporarily relocated (Aqua and Verizon)
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 16: Temporary Pedestrian Bridge (ADA Compliant) * Conceptual Only – May be redesigned by Contactor (design/build)
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 17: Stage 1B (2nd Half 2024) - Temporary Shielding - Temporary Shoring - Demo (deck and beams) - Utilities to be temporarily relocated (Aqua and Verizon)
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 18: Stage 1B (2nd Half 2024) - Temporary Shoring to be installed to keep Hinckley Ave. open
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 19: Stage 1B (2nd Half) - Temporary Shielding to be installed to protect AMTRAK from falling debris
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 20: Stage 1B (2nd Half 2024) - Demo - Sawcut and remove deck, beams and backwall
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 21: Stage 1B (2nd Half 2024) Counterweight Walls and Pedestal - Front Face of Existing Stone Wall to Remain - Drill Dowels - Form / Rebar / Pour Class A Concrete CW Wall
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 22: Stage 1B (2nd Half 2024) - Set (10) Pre-Cast Beams - Installation of new 10” water line and communication lines - Form / Rebar/ Pour Deck - 14-day wet cure - Form / Rebar / Pour Sidewalks - Form / Rebar / Pour Barrier - Install Luminaires and Fencing - Approach Slabs and Sidewalks
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 23: Stage 1B (2nd Half 2024) Set Pre-Cast Beams Includes the installation of new 10” water line and communication lines
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 24: Stage 2 (2025)
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 25: Stage 2 (2025) - Closes Traffic on E. Ridley Ave. between Swarthmore Ave. and Thayer Ave. - Closes Traffic on E. Ward Ave between and Cresswell St. and the Bridge - All Residential Access must be Maintained by the Contractor
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 26: Stage 2 (2025) - Utilities - Relocate Gas and Water - Signal Improvement at Swarthmore and Ridley Ave - Drainage Improvements - Curb, Sidewalk and ADA Ramps - Full Depth Reconstruction - Landscape Improvements
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 27: Stage 2 (2025) - Utilities - Relocate Gas and Water -
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 28: Stage 3A (1st Quarter 2026)
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 29: Stage 3A (1st Quarter of 2026) - Closes Traffic on Hinckley Ave. from Morton Ave. west - Closes Traffic on Sellers Ave between and Hinckley Ave. and the Bridge - All Residential Access must be Maintained by the Contractor
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 30: Stage 3A (1st Quarter of 2026) - Utilities - Relocate Gas - Drainage Improvements - Signal Improvements at Sellers Ave. and Swarthmore Ave. - Curb, Sidewalk, Pavers and ADA Ramps - Full Depth Reconstruction - Landscape Improvements
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 31: Stage 3A (1st Quarter of 2026) -
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 32: Stage 3B (2nd Quarter of 2026)
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 33: Stage 3B (2nd Quarter of 2026) - Closes Traffic the eastbound shoulder E. Ridley Ave. - Closes Traffic the westbound shoulder E. Hinkley Ave. - All Residential Access must be Maintained by the Contractor
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)

## Slide 34: Stage 3B (2nd Quarter of 2026) - Remove Temp. Bridge - Form/Rebar/Pour kneewalls and barrier for Bridge – Tie-In Piece - Install bridge fencing - Final sidewalk and landscaping ANTICIPATED OPEN BRIDGE ON JULY 1, 2026
Notes: TITLE SLIDE – SEE COMMENTS (go to the review tab and click on show comments)